## Original RACI
# | Item | Action | Responsibility |  | Deadline | Format Given By BOC? | Format Attached? | Remarks
|  |  | i-exceed | NBL
1 | General Conditions | Decision on JV or Consortium | X | X | 2023-10-08
|  | Delivery - Roles and Responsibility Matrix | X | X | 2023-10-11
|  | Undestanding of Evaluation and Qualification Criteria | X | X | 2023-10-11
|  | Priliminary Validate of Technical and Functional Specification | X |  | 2023-10-11
|  | Confirmation on Priliminary validation of Condition of Contract | X | X | 2023-10-13
<n+>
2 | Pre-Bid Meeting | Any points to be discussed to be shared with N-able | X |  | 2023-10-08 | Yes | Yes
|  | Attending Pre-bid meeting |  |  | 2023-10-09
|  | Followup on Feedback - items discussed at Pre-bid meeting |  | X | 2023-10-16
3 | Clarifications | Clarifications shared with N-able | X |  | 2023-10-08 | Yes | Yes
|  | Clarifications shared with BOC |  | X | 2023-10-09
|  | BOC response shared with OEM |  |  | 2023-10-16
4 | JV/ Consortium Validity | Share Templates with Legal for validity and amendments: - Letter (Intend to Sign a JV) - Draft JV Agreement - Draft Teaming Agreement - Board Resolution - Affidavit - Signatory Authorization to Asiri |  | X | 2023-10-10 | No | No
|  | Obtain draft from Legal (all above) |  | X | 2023-10-10
|  | Share Drafts with OEM |  | X | 2023-10-12
|  | Resolve Clarifications and asisist in Finalization | X | X | 2023-10-16
|  | Review shared documents | X |  | 2023-10-18
|  | Obtain Final Legal documents | X |  | 2023-10-20
5 | PCA | Request and obtain PCA as stipulated |  | X | 2023-10-04
6 | MAF | Share MAF Template with OEM |  | X | 2023-10-10 | Yes | Yes
|  | Obtain MAF, scan and folder it | X |  | 2023-10-22 | Yes | Yes
7 | Bid bond for LKR 2M | Internal approval and Form submission |  | X | 2023-10-09 | Yes | Yes | Handed over to finance based on final selection.
|  | Request from bank |  | X | 2023-10-09 |  |  | Bank requested 3 working days to handover bond
|  | Bond Collection from bank |  | X | 2023-10-11
8 | Bid Submission | Preperation of Cover pages/ Submission Folders and Separators |  | X | 2023-10-11 | No | No
|  | Validation of Bid Submission Folder and Content | S | X | 2023-10-24
|  | Printing & packing bid | S | X | 2023-10-24
|  | Submission of bid |  | X | 2023-10-25
|  | Feedback on bid submission findings |  | X | 2023-10-25
9 | Qualification criteria response and Other Mandatory Documents | The Bidder or any party/parties of the Bidder should not be on the list of Defaulting Contractors of the Government of Sri Lanka or of the Bank of Ceylon. | X | X | 2023-10-18 | Yes | Yes
|  | Bidder or its Related Companies should not have a conflict of interest relate to the business domain of the Bank within Sri Lanka. | X | X | 2023-10-18 | Yes | Yes
|  | In case of Joint Venture / Consortium, each party of the Joint Venture / Consortium should have a minimum annual turnover of LKR 250 Million or equivalent in foreign currencies minimum in three financial years, within last five financial years, including recent two financial years (2020/2021 and 2021/2022) and should be profit-making entities with a positive net worth in recent year (2021/22). | X | X | 2023-10-18 | Yes | Yes
|  | In case of individual Bidder, the Bidder should have experience in implementing Internet Mobile Banking Solution/s having complexities and features either similar or exceeding the proposed solution in minimum three (03) local or international commercial banks within last five (05) years up to the bid closing date. | X | X | 2023-10-18 | Yes | Yes
|  | In case of Joint Venture / Consortium, the local partner of the Joint Venture / Consortium should have implemented similar banking solution in minimum one local or international bank within last 5 years, up to the bid closing dates, with an active maintenance contract. | X | X | 2023-10-18 | Yes | Yes
|  | The proposed Solution should have been supplied, installed, commissioned and is being actively maintained in minimum 03 financial institutions globally within last 05 years up to the bid closing date. | X | X | 2023-10-18 | Yes | Yes
10 | Technical Specification Compliance | Preparing compliance statement for the requirements given in Section V as per the format given "Techncial and Functional Requirements" | X |  | 2023-10-11 | Yes | Yes
|  | Ensuring compliance responses are given as S/C/A/U as indicated in Section III | X | X | 2023-10-20 | Yes | Yes
|  | Sharing completed compliance with N-able | X |  | 2023-10-22 | Yes | Yes
11 | Software license Bill of Materials | Derive the i-exceed software license requirement in line with recommended number of environments and prepare the Bill of Materials.
12 | Middleware sizing and bill of materials | Identify a cost effective suite of middleware licenses required to support the i-exceed software and provide N-able so that they can get the pricing from respective OEMs. This will include any application servers, API management software, Identity and Access Management software (if required) etc.
13 | Hardware sizing and minimum hardware Recommentation as Bill of Materials | Derive the sizing of the required hardware including servers, storage, load balancers and come up with detailed requirement specification (e.g. server - CPU/memory/processor architecture, storage - capacity and IOPS etc.). N-able will have to generate the Bill of Materials to be included in the response. | X | X | 2023-10-20 | Yes | Yes
16 | Bidding Forms:
| Section I | Instruction to Bidders (ITB) |  | X | 2023-10-10 | Yes | Yes
| Section II | Bidding Datasheets (BDS) |  | X | 2023-10-10 | Yes | Yes
|  | Lette of Technical Bid (Summerized version of Bid Submission Form) |  | X | 2023-10-10 | Yes | Yes
| Section III | Evaluation and Qualification Criteria |  | X | 2023-10-10 | Yes | Yes
| Section IV | Bid Particulars of Bid |  | X | 2023-10-10 | Yes | Yes
|  | Bidder Profile | X | X | 2023-10-16 | Yes | Yes
|  | Bidder's Details | X | X | 2023-10-16 | Yes | Yes
|  | Compliance Certificate and Affidavit | X | X | 2023-10-16 | Yes | Yes
|  | Authorization to Sign the Bidding Form | X | X | 2023-10-16 | Yes | Yes
|  | JV Agreement (Draft) | X | X | 2023-10-16
|  | Letter of Intent for JV | X | X | 2023-10-16
|  | MAF | X |  | 2023-10-16 | Yes | Yes
|  | Bid Security |  | X | 2023-10-11 | Yes | Yes
|  | Speciemen for Response (Technical and Functional) | X |  | 2023-10-18 | Yes | Yes
|  | Methodology and Detailed Project Plan | X | X | 2023-10-18 | Yes | Yes
|  | Bill of Materials | X | X | 2023-10-18 | Yes | Yes
|  | Letter of Authorization to Attent Tender Opening |  | X | 2023-10-10 | Yes | Yes
|  | Litigation History | X | X | 2023-10-16 | Yes | Yes
17 | Detailed solution document | Shall explain how the components of the solution would stack up to deliver the target requirement specifications given under functional and non-functional requirements of the RFP | X |  | 2023-10-17 | No | No
| Approach, methodology, tools used during the implementation | Explain the project delivery approach and methodology to be adopted | X |  | 2023-10-17 | No | No
| Statement of Work and Deliverables | Clearly defining the activties to be performed | X |  | 2023-10-17 | No | No
| Detailed System Rollout plan | Detailed System Rollout plan | X |  | 2023-10-17 | No | No | Additional documents to be provided
| Document enphasizing the UI/UX standardisation adoptation and emphasis. | Description of how the platform can be used to standardize the UI/UX across customer journeys and across Internet and Mobile banking experience | X |  | 2023-10-17 | No | No
| Training plan | Need to capture the expectation of best practices of the Bank from the RFP and explain how the proposed platform can help implement those practices. This should include detailed training schedule and areas covered by the training | X |  | 2023-10-17 | No | No
| Project Management plan | Project Management, Change Management and Migration Plan | X |  | 2023-10-17 | No | No
| Data migration strategy and plan | Details of how we proposed to migrate master data and transaction data from the existing Internet & Mobile Banking application
| Pricing | In the pricing formats given in the tender |  |  | 2023-10-23 | No | No
| Market trends and best practices | What are the trends in Internet & Mobile Banking and how will be platform allow the Bank to meet the demands of those trends | X |  | 2023-10-17 | No | No
| Intermediate deliverables | If there are deliverables in between the major milestones identified in the SOW, we need to state them here | X |  | 2023-10-17 | No | No
| Customer references | Details of the references to simila implementations in line with the guidelines and criteria given in the RFP (Minimum of 3 - 5) | X | X | 2023-10-13 | Yes | Yes
| Additional documents | Letter of authorization to sign/commit the bidder should be annexed (Letter authorizing N-able to sign the bid forms on behalf of the JV) | X |  | 2023-10-17 | No | No
|  | Sample contract agreement should be submitted by the bidder | X |  | 2023-10-17 | No | No
|  | Any additional services provided should be clearly stated | X |  | 2023-10-20 | No | No
|  | Referances as per the given guidelines and Criteria (Min on 3 - 5) | X | X | 2023-10-13 | Yes | Yes
|  | Consent to obtain Approval Letter (Min with a weeks prior notice) | X | X | 2023-10-20 | Yes | Yes
|  | Should declare the names of current directors and shareholders | X |  | 2023-10-17 | No | No
|  | Letter confirming that the bidder is in conformity with the laws and regulations with regard to the elimination of forced/compulsory labor and the abolition of child labor. | X |  | 2023-10-17 | No | No
|  | Applicable Design and Architectural (Application and HW) documents | X |  | 2023-10-17 | No | No
|  | Gartner magic quadrant (if available) and other accreditation | X |  | 2023-10-17 | No | No

## Technical bid deliverables
| Item | Action | Ask from i-exceed (Technical bid deliverables)
1 | General Conditions | Decision on JV or Consortium
Delivery - Roles and Responsibility Matrix
Undestanding of Evaluation and Qualification Criteria
Priliminary Validate of Technical and Functional Specification
Confirmation on Priliminary validation of Condition of Contract
Any points to be discussed to be shared with N-able
2 | Pre-Bid Meeting | Attending Pre-bid meeting
Followup on Feedback - items discussed at Pre-bid meeting
Clarifications shared with N-able
3 | Clarifications | Clarifications shared with BOC
BOC response shared with OEM
Share Templates with Legal for validity and amendments: - Letter (Intend to Sign a JV) - Draft JV Agreement - Draft Teaming Agreement - Board Resolution - Affidavit - Signatory Authorization to Asiri
4 | JV/ Consortium Validity | Obtain draft from Legal (all above)
Share Drafts with OEM
Resolve Clarifications and asisist in Finalization
Review shared documents
Obtain Final Legal documents
Request and obtain PCA as stipulated
5 | PCA | Share MAF Template with OEM
6 | MAF | Obtain MAF, scan and folder it
Internal approval and Form submission
7 | Bid bond for LKR 2M | Request from bank
Bond Collection from bank
Preperation of Cover pages/ Submission Folders and Separators
8 | Bid Submission | Validation of Bid Submission Folder and Content
Printing & packing bid
Submission of bid
Feedback on bid submission findings
The Bidder or any party/parties of the Bidder should not be on the list of Defaulting Contractors of the Government of Sri Lanka or of the Bank of Ceylon.
9 | Qualification criteria response and Other Mandatory Documents | Bidder or its Related Companies should not have a conflict of interest relate to the business domain of the Bank within Sri Lanka.
In case of Joint Venture / Consortium, each party of the Joint Venture / Consortium should have a minimum annual turnover of LKR 250 Million or equivalent in foreign currencies minimum in three financial years, within last five financial years, including recent two financial years (2020/2021 and 2021/2022) and should be profit-making entities with a positive net worth in recent year (2021/22).
In case of individual Bidder, the Bidder should have experience in implementing Internet Mobile Banking Solution/s having complexities and features either similar or exceeding the proposed solution in minimum three (03) local or international commercial banks within last five (05) years up to the bid closing date.
In case of Joint Venture / Consortium, the local partner of the Joint Venture / Consortium should have implemented similar banking solution in minimum one local or international bank within last 5 years, up to the bid closing dates, with an active maintenance contract.
|  | The proposed Solution should have been supplied, installed, commissioned and is being actively maintained in minimum 03 financial institutions globally within last 05 years up to the bid closing date. | Please provide three of the closest references in the last five years that you have implemnted and currently being maintained.
|  | Preparing compliance statement for the requirements given in Section V as per the format given "Techncial and Functional Requirements" | Already finalized today, please update the discussed items and share the final version
10 | Technical Specification Compliance | Ensuring compliance responses are given as S/C/A/U as indicated in Section III | Referring to the same as above
|  | Sharing completed compliance with N-able | Referring to the same as above
|  | Derive the i-exceed software license requirement in line with recommended number of environments and prepare the Bill of Materials. | Please share with us the software bill of materials and any open source components that are included in the product and actively supported by i-exceed (ElasticSearch, Logstash, Tomcat, InnoDB etc.)
11 | Software license Bill of Materials | Identify a cost effective suite of middleware licenses required to support the i-exceed software and provide N-able so that they can get the pricing from respective OEMs. This will include any application servers, API management software, Identity and Access Management software (if required) etc. | In terms of middleware N-able will be proposing only PostgreSQL Server subscriptions and WSO2 API Manager subscriptions. Please confirm that no other middleware licenses/subscriptions are required.
12 | Middleware sizing and bill of materials | Derive the sizing of the required hardware including servers, storage, load balancers and come up with detailed requirement specification (e.g. server - CPU/memory/processor architecture, storage - capacity and IOPS etc.). N-able will have to generate the Bill of Materials to be included in the response. | Sizing has been shared and the bill of materials will be prepared by N-able. Please share with us the transaction profiling that you typically use for your sizing including indicative percentages as discussed on 24/10/2023
13 | Hardware sizing and minimum hardware Recommentation as Bill of Materials | How we carried out the sizing | Details of our sizing methodology shall be outlined here
16 | Bidding Forms: | Instruction to Bidders (ITB)
| Section I | Bidding Datasheets (BDS)
| Section II | Lette of Technical Bid (Summerized version of Bid Submission Form)
Evaluation and Qualification Criteria
| Section III | Bid Particulars of Bid
| Section IV | Bidder Profile
Bidder's Details
Compliance Certificate and Affidavit
Authorization to Sign the Bidding Form
JV Agreement (Draft)
Letter of Intent for JV
MAF
Bid Security
Speciemen for Response (Technical and Functional)
|  | Methodology and Detailed Project Plan | Addressed elsewhere, no need to attend to
|  | Bill of Materials | Addressed elsewhere, no need to attend to
Letter of Authorization to Attent Tender Opening
Litigation History
|  | Shall explain how the components of the solution would stack up to deliver the target requirement specifications given under functional and non-functional requirements of the RFP | Please re-validate if the required contents are included in the shared Technical Proposal. In the meantime, our team will also review.
17 | Detailed solution document | Explain the project delivery approach and methodology to be adopted | Some mentioning of the approach is included in the Technical proposal. However, the expectation is that this is provided as a separate document on its own.
| Approach, methodology, tools used during the implementation | Clearly defining the activties to be performed | Please break down the scope of work into a separate document outside the technical proposal. Do not mentioned any financial terms in this document including payment terms.
| Statement of Work and Deliverables | Detailed System Rollout plan | Plan for the overall rollout of the solution. Can we connected to the Approach & Methodology document.
| Detailed System Rollout plan | Description of how the platform can be used to standardize the UI/UX across customer journeys and across Internet and Mobile banking experience | Please provide this as a separate document. Your proposal to UI/UX standardization. Part of this is mentioned in the technical proposal. We need to provide this as a separate document.
| Document enphasizing the UI/UX standardisation adoptation and emphasis. | Need to capture the expectation of best practices of the Bank from the RFP and explain how the proposed platform can help implement those practices. This should include detailed training schedule and areas covered by the training | Details are given in the Technical proposal. Please present this as a separate document.
| Training plan | Project Management, Change Management and Migration Plan | Provide this as a separate document.
| Project Management plan | Details of how we proposed to migrate master data and transaction data from the existing Internet & Mobile Banking application | Provide this as a separate document.
| Data migration strategy and plan | In the pricing formats given in the tender
| Pricing | What are the trends in Internet & Mobile Banking and how will be platform allow the Bank to meet the demands of those trends | Provide this as a separate document.
| Market trends and best practices | If there are deliverables in between the major milestones identified in the SOW, we need to state them here
| Intermediate deliverables | Details of the references to simila implementations in line with the guidelines and criteria given in the RFP (Minimum of 3 - 5) | Provide the customer references as a separate document in the format mentioned in the tender
| Customer references | Letter of authorization to sign/commit the bidder should be annexed (Letter authorizing N-able to sign the bid forms on behalf of the JV)
| Additional documents | Sample contract agreement should be submitted by the bidder
Any additional services provided should be clearly stated
|  | Referances as per the given guidelines and Criteria (Min on 3 - 5) | This is the same as customer references
Consent to obtain Approval Letter (Min with a weeks prior notice)
Should declare the names of current directors and shareholders
Letter confirming that the bidder is in conformity with the laws and regulations with regard to the elimination of forced/compulsory labor and the abolition of child labor.
|  | Applicable Design and Architectural (Application and HW) documents | Components diagram of the application and the proposed deployment architecture (Diagram 4.3.4 in the technical proposal is generic, please include all components proposed for including ELK stack, InnoDB, web server tier etc. clearly labelling middleware components)
|  | Gartner magic quadrant (if available) and other accreditation | Shareable reprints of documentation that evaluates the proposed product from vendor independent entities